## Mon & Eval
Goals, Outcomes and Outputs |  | Indicators (what will you measure?) | Method/ source of data (how will you measure?) | Location (where will monitoring be done?) | When (timeframe & frequency of data collection) | Who to provide and use (who will provide and analyse the data?) | Baseline data (most recent figure and date, or when it will be defined) | Planned intermediate result |  |  | Planned final result (value and date) | Cost | Reporting
[8 empty] | Cal 2021 | Cal 2022 | Cal 2023
Goal - to save (min 120) threatened Australian native wildflower species from extinction. | [12 empty] | 2021 |  |  |  |  | 2022 |  |  |  |  | 2023
Overall Result | [12 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | 2021 Totals | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | 2021+2022 Totals | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | 2021+2022+2023 Totals | Target met? | Comments
Outcome 1 | proactively conserve seed from at least 120 distinct Australian native wildflowers in seed banks, for long term conservation, research and restoration.
Output #1 | Improved genetic diversity of seed collections across Australia | # species banked (including previously unbanked species, species where established collections have added genetic diversity, and species where duplicate collections were made). | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | tbc | 20-40 | 20-40 | 20-40 | 100 |  | on track | 22 | 0 | 25 | 39 (duplicate collections of the same species were taken across the four quarters) | 23 | 10 | 0 | 7 | 72 (duplicate collections of the same species were taken across the project) | 32 | 20 | 3 | 27 | 153 (duplicate collections of the same species were taken across the project) | Yes
|  | # different states/territories represented in collections | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 7 | 7 | 7 | 7 | 7 |  | 6 | 5 | 0 | 4 | 6 (ACT/NSW/WA/TAS/Vic/SA) | 6 | 2 | 0 | 2 | 6 (ACT/NSW/WA/TAS/Vic/SA) | 5 | 4 | 1 | 2 | 6 (ACT/NSW/WA/TAS/Vic/SA/NT) | Yes
|  | # species that are endemic (native and restricted to Australia) | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | tbc | 35 | 25 | 25 | 85 |  | on track | 21 | 0 | 24 | 38 (duplicate collections of the same species were taken across the four quarters) | 23 | 10 | 0 | 7 | 71 (duplicate collections of the same species were taken across the project) | 32 | 16 | 3 | 27 | 147 (duplicate collections of the same species were taken across the project) | Yes
|  | # of collections | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | tbc | 20-40 | 20-40 | 20-40 | 100 |  | on track | 36 | 0 | 40 | 76 | 38 | 19 | 0 | 8 | 141 | 48 | 43 | 4 | 28 | 262 | Yes
|  | # different localities/provenances/populations represented in collections | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | tbc | 20-40 | 20-40 | 20-40 | 100 |  | on track | 34 | 0 | 38 | 72 | 36 | 15 | 0 | 7 | 130 | 48 | 36 | 3 | 28 | 245 | Yes
|  | # collections considered large enough to be a conservation collection | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 20-40 | 20-40 | 20-40 | 100 |  | on track | 28 | 0 | 40 | 68 | 30 | 11 | 0 | 6 | 115 | 42 | 20 | 1 | 26 | 204 | Yes
|  | # of threatened species (state/territory) collected | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 18 | 16 | 16 | 50 |  | on track | 12 | 0 | 13 | 25 (duplicate collections of the same species were taken across the four quarters) | 13 | 1 | 0 | 1 | 38 (duplicate collections of the same species were taken across the project) | 27 | 7 | 1 | 1 | 73 (duplicate collections of the same species were taken across the project) | Yes
|  | # of threatened species (commonwealth) collected | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 6 | 5 | 4 | 15 |  | on track | 2 | 0 | 12 | 14 (duplicate collections of the same species were taken across the four quarters) | 8 | 0 | 0 | 1 | 21 (duplicate collections of the same species were taken across the project) | 18 | 0 | 1 | 0 | 40 (duplicate collections of the same species were taken across the project) | Yes
Output #2 | Ensuring collections are valid. Build knowledge. | # distinct species tested. (Note this could be newly collected species or existing species in seed banks that require new trials) | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 10-20 | 10-20 | 10-20 | 30 |  | on track | 4 | 9 | 1 | 12 | 1 | 6 | 15 | 2 | 35 | 9 | 7 | 8 | 13 | 66 | Yes
|  | #Germination Trials conducted | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 10-20 | 10-20 | 10-20 | 30 |  | on track | 13 | 27 | 1 | 39 | 2 | 11 | 46 | 6 | 104 | 23 | 13 | 11 | 67 | 218 | Yes
|  | # germination protocols established | Reporting Data Spreadsheet | All locations | Report quarterly | ASBP | 0 | 10-20 | 10-20 | 10-20 | 30 |  | on track | 4 | 8 | 1 | 11 (duplicate protocols for the same species were reported in each quarter) | 1 | 6 | 11 | 1 | 29 | 6 | 7 | 7 | 12 | 56 | Yes
Output #3 | re-introduction | # propagated for living collections (with list species) | Reporting Data Spreadsheet | All locations | 6 months | ASBP | 0 | 1 | 1 | 1 | 3 |  | on track | 0 | 2 species, 550 plants (Brachyscome muelleri [500] and Podolepis jaceoides [50]) | 0 | 2 species, 550 plants (Brachyscome muelleri [500] and Podolepis jaceoides [50]) | 1 species, 2000 plants (Actinotus forsythii [2000]) | 0 | 3 Species, 330 plants (Caladenia busselliana [100], Cheiranthera volubilis [130], Mentha atrolilacina [100]) | 0 | 6 species, 2880 plants (Brachyscome muelleri [500], Podolepis jaceoides [50], Actinotus forsythii [2000], Caladenia busselliana [100], Cheiranthera volubilis [130], Mentha atrolilacina [100]) | 0 | 0 | 1 species, 70 plants (Pelargonium sp. Striatellum (G.W.Carr 10345)) | 1 species, 60 plants (Olearia quercifolia) | 8 species, 3010 plants (Brachyscome muelleri [500], Podolepis jaceoides [50], Actinotus forsythii [2000], Caladenia busselliana [100], Cheiranthera volubilis [130], Mentha atrolilacina [100], Pelargonium sp. Striatellum (G.W.Carr 10345) [70], Olearia quercifolia [60]) | Yes
|  | # propagated for re-introduction (with list species) | Reporting Data Spreadsheet | All locations | Annually | ASBP | 0 | 2 | 1 | 1 | 4 |  | on track | on track | 3 species, 770 plants (Swainsona pyrophila [100], Brachyscome muelleri [500], Coronidium gunnianum [170]) | 0 | 3 species, 770 plants (Swainsona pyrophila [100], Brachyscome muelleri [500], Coronidium gunnianum [170]) | 0 | 0 | 1 species, 300 plants (Phebalium calcicola [300]) | 0 | 4 species, 1070 plants (Swainsona pyrophila [100], Brachyscome muelleri [500], Coronidium gunnianum [170], (Phebalium calcicola [300]) | 1 Species, 360 plants (Caladenia busselliana [360]) | 0 | 0 | 0 | 5 species, 1430 plants (Swainsona pyrophila [100], Brachyscome muelleri [500], Coronidium gunnianum [170], (Phebalium calcicola [300], (Caladenia busselliana [360]) | Yes
|  | # total reintroduction events (via RB i.e. reallocation; volunteers; and additional funding) | Reporting Data Spreadsheet | All locations | Annually | ASBP | 0 | 2 | 1 | 1 | 4 |  | on track | on track | 4 events - Swainsona pyrophila at Secret Rocks Nature Reserve on 04/08/2021 - Brachyscome muelleri at Secret Rocks Nature Reserve on 04/08/2021 - Coronidium gunnianum at Lobethal Bushland Park on 02/06/2021 - Coronidium gunnianum at Billy Goat Hill on 02/06/2021 | 0 | 4 events - Swainsona pyrophila at Secret Rocks Nature Reserve on 04/08/2021 - Brachyscome muelleri at Secret Rocks Nature Reserve on 04/08/2021 - Coronidium gunnianum at Lobethal Bushland Park on 02/06/2021 - Coronidium gunnianum at Billy Goat Hill on 02/06/2021 | 0 | 0 | 1 event - Phebalium calcicola in Kongorong area of South Australia in 08/2022 | 0 | 5 events - Swainsona pyrophila at Secret Rocks Nature Reserve on 04/08/2021 - Brachyscome muelleri at Secret Rocks Nature Reserve on 04/08/2021 - Coronidium gunnianum at Lobethal Bushland Park on 02/06/2021 - Coronidium gunnianum at Billy Goat Hill on 02/06/2021 - Phebalium calcicola in Kongorong area of South Australia in 08/2022 | 1 event - Caladenia busselliana in its historic range of WA in march 2023 | 0 | 0 | 0 | 6 events - Swainsona pyrophila at Secret Rocks Nature Reserve on 04/08/2021 - Brachyscome muelleri at Secret Rocks Nature Reserve on 04/08/2021 - Coronidium gunnianum at Lobethal Bushland Park on 02/06/2021 - Coronidium gunnianum at Billy Goat Hill on 02/06/2021 - Phebalium calcicola in Kongorong area of South Australia in 08/2022 - Caladenia busselliana in its historic range of WA in march 2023 | Yes
|  | # distinct species reintroduced (via RB i.e. reallocation; volunteers; and additional funding) | Reporting Data Spreadsheet | All locations | Annually | ASBP | 0 | 2 | 1 | 1 | 4 |  | on track | on track | 3 species (Swainsona pyrophila, Brachyscome muelleri, Coronidium gunnianum) | 0 | 3 species (Swainsona pyrophila, Brachyscome muelleri, Coronidium gunnianum) | 0 | 0 | 1 species (Phebalium calcicola) | 0 | 4 species (Swainsona pyrophila, Brachyscome muelleri, Coronidium gunnianum, Phebalium calcicola) | 1 Species, (Caladenia busselliana) | 0 | 0 | 0 | 5 species (Swainsona pyrophila, Brachyscome muelleri, Coronidium gunnianum, Phebalium calcicola, Caladenia busselliana) | Yes
|  | wherever feasible, total area of planting areas supported by to the project during the term | Reporting Data Spreadsheet | All locations | Annually | ASBP | 0 | up to 50sq feet | up to 50sq feet | up to 50sq feet | Up to 150 sq feet |  | on track | on track | 6232 sq feet (579 sq m) | 0 | 6232 sq feet (579 sq m) | 387 sq feet (36 sq m) | 0 | 1195 sq feet (111 sq m) | 0 | 7815 sq feet (726 sq m) | 258 sq feet (24 sq m) | 0 | 0 | 215 sq feet (20 sq m) | 8288 sq feet (770 sq m) | Yes
Output #4 | Corunna Daisy Specific | # of plants in each site | Reporting Data Spreadsheet | South Australia | Report quarterly | ASBP | 0 | 50-100 | N/A | N/A | 50-100 |  | on track | on track | 250 planted at Secret Rocks Nature Reserve. 500 in seed orchard at Adelaide Botanic Gardens | 0 | 250 planted at Secret Rocks Nature Reserve. 500 in seed orchard at Adelaide Botanic Gardens | 0 | Activation now Complete | Activation now Complete | Activation now Complete | 250 planted at Secret Rocks Nature Reserve. 500 in seed orchard at Adelaide Botanic Gardens | Activation now Complete | Activation now Complete | Activation now Complete | Activation now Complete | 250 planted at Secret Rocks Nature Reserve. 500 in seed orchard at Adelaide Botanic Gardens | Yes
|  | Size of area for translocation sites | Reporting Data Spreadsheet | South Australia | Report quarterly | ASBP | 0 | 30m2 | N/A | N/A | 30m2 |  | on track | on track | 30m2 | 0 | 30m2 | 0 | Activation now Complete | Activation now Complete | Activation now Complete | 30m2 | Activation now Complete | Activation now Complete | Activation now Complete | Activation now Complete | 30m2 | Yes
|  | # of replicates (sites) | Reporting Data Spreadsheet | South Australia | Report quarterly | ASBP | 0 | 5 | N/A | N/A | 5 |  | on track | on track | 5 sites (4 at Secret Rocks reserve and 1 at the Adelaide Botanic Garden) | 0 | 5 sites (4 at Secret Rocks reserve and 1 at the Adelaide Botanic Garden) | 0 | Activation now Complete | Activation now Complete | Activation now Complete | 5 sites (4 at Secret Rocks reserve and 1 at the Adelaide Botanic Garden) | Activation now Complete | Activation now Complete | Activation now Complete | Activation now Complete | 5 sites (4 at Secret Rocks reserve and 1 at the Adelaide Botanic Garden) | Yes
|  | # seedlings emerged/# flowering/seeding | Reporting Data Spreadsheet | South Australia | Report quarterly | ASBP | 0 | 500 | N/A | N/A | 500 |  | on track | on track | 1000 seedlings/500 flowering/500 seeding | 0 | 1000 seedlings/500 flowering/500 seeding | 0 | Activation now Complete | Activation now Complete | Activation now Complete | 1000 seedlings/500 flowering/500 seeding | Activation now Complete | Activation now Complete | Activation now Complete | Activation now Complete | 1000 seedlings/500 flowering/500 seeding | Yes
Output #5 | Bussell’s Spider orchid Specific | # plants propagated and maintained in the seed orchard | Reporting Data Spreadsheet | Western Australia | Report quarterly | ASBP | 0 | 0 | 50-100 | 0 | 50-100 31 Nov 2023 | [8 empty] | 75 | 0 | 75 | 0 | 0 | Activation now Complete | Activation now Complete | 75 | Yes
|  | # habitat surveys completed | Reporting Data Spreadsheet | Western Australia | Report quarterly | ASBP | 0 | 0 | 5 sites and min. 5 replicate surveys each (25 surveys) | 0 | 5 sites 31 Nov 2023 | [8 empty] | 1 site (5 replicates) | 6 sites (5 reps each) | 7 site (5 replicates each) | 0 | 0 | Activation now Complete | Activation now Complete | 7 site (5 replicates each) | Yes
|  | # translocation sites | Reporting Data Spreadsheet | Western Australia | Report quarterly | ASBP | 0 | 0 | 1 | 0 | 1 31 Nov 2023 | [8 empty] | 0 | 1 new site identified | 1 new site identified | 0 | 0 | Activation now Complete | Activation now Complete | 1 new site identified | Yes
|  | # plants translocated at each site | Reporting Data Spreadsheet | Western Australia | Report quarterly | ASBP | 0 | 0 | 360 | 0 | 360 31 Nov 2023 | [8 empty] | 0 | 0 | 0 | 216 plants at 1 site | 0 | Activation now Complete | Activation now Complete | 216 plants at 1 site | No | Due to the unexpected change in the translocation site in Q4 2022, only 216 of the 360 plants were planted given the smaller available area. The additional plants will be translocated in future seasons.
Output #6 | Omeo Stork's-bill Specific | Amount of seed collected | Reporting Data Spreadsheet | NSW | Report quarterly | ASBP | 0 | 0 | 0 | 362 | 362 31 Jan 2023 | [13 empty] | 362 seeds | Activation now Complete | 362 seeds | Yes
|  | # Germination protocols established | Reporting Data Spreadsheet | ACT | Report quarterly | ASBP | 0 | 0 | 0 | 1 | 1 30 Sept 2023 | [13 empty] | 1 protocol | Activation now Complete | 1 protocol | Yes
|  | # plants planted in living collections | Reporting Data Spreadsheet | ACT | Report quarterly | ASBP | 0 | 0 | 0 | 20-50 | 20 30 Sept 2023 | [13 empty] | 68 planted | Activation now Complete | 68 planted | Yes
|  | # planting sites (living collections) | Reporting Data Spreadsheet | ACT | Report quarterly | ASBP | 0 | 0 | 0 | 2 | 2 30 Sept 2023 | [13 empty] | 2 living collections at the ANBG | Activation now Complete | 2 living collections at the ANBG | Yes
MAIN OUTCOME | Program total goal | # distinct species supported by program (i.e. seed collected, germination trial or planting, or a mix of the above) i.e. this figure substantiates "Botanica is helping save 120 threatened wildflower species" | combination of all distinct species worked on in the period | All locations | 6 months | ASBP | 0 | 31-61 | 31-61 | 31-61 | 120 |  | on track | 26 | 9 | 26 | 42 (See Data report, 'Distinct Sp Supported' Tab for list) | 27 | 10 | 18 | 15 | 87 (See Data report, 'Distinct Sp Supported' Tab for list) | 34 | 26 | 7 | 50 | 183 (See Data report, 'Distinct Sp Supported' Tab for list) | Yes
Outcome 2 | millions of Australians engaged and educated about the importance of flora conservation and securing biodiversity to future-proof Australia | [15 empty] | 42
Output #1 | Press coverage | # of stories covered | media tracker |  |  | WWF/ RB | 0 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | # of outlets sharing stories | media tracker |  |  | WWF/ RB | 0 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | overall sentiment | survey/ sampling |  |  | WWF/ RB | neutral | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Output #2 | Botanica campaign | reach of activities (mentioning ASBP) | Google Analytics; social media data; in-store data |  |  | WWF/ RB | 0 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | engagement of activities (mentioning ASBP) | Google Analytics; social media data; in-store data |  |  | WWF/ RB | 0 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Output #3 | ASBP following | # unique visits to ASBP Website | Google Analytics |  | Report quarterly | ASBP | 0 | [5 empty] | 2,362 (01 Jan to 31 March) | 2,300 (01 April to 30 June) | 1,489 (01 July to 30 September) | 1,324 (01 October to 31 December) | 7475 | 1,008 (01 Jan to 18 March) | 1,912 (19 March to 14 June) | 2,468 (15 June to 30 September) | 1,344 (01 October to 31 December) | 14304 | 1,318 (01 Jan to 25 March) | 1,401 (26 March to 30 June) | N/A - google Analytics was'nt avaiable for this period | 1,389 (01 October to 31 December) | 25887
|  | increase in social media reach | Social media data |  | Report quarterly | ASBP | tbc | [5 empty] | 820 (Facebook) 70 (Instagram) (01 Jan to 31 March) | 8,517 (Facebook) 5,575 (Instagram) (01 April to 30 June) | 6,141 (Facebook) 186 (Instagram) (01 July to 30 September | 5,312 (Facebook) 240 (Instagram) (01 October to 31 December) | 18,100 (Facebook) 5,797 (Instagram) | 926 (Facebook) 216 (Instagram) (01 Jan to 18 March) | 69,400 (Facebook) 734 (Instagram) (19 March to 14 June) | 5,200 Facebook) 903 (Instagram) (15 June to 30 September) | 105.500 (Facebook) 217 (Instagram) (01 October to 31 December) | 192,100 (Facebook) 7,017 (Instagram) | 2,252 (Facebook) 260 (Instagram) (01 Jan to 25 March) | 185,606 (Facebook) 15,039 (Instagram) (26 March to 30 June) | 6,233 (Facebook) 906 (Instagram) (1 July - 26 Sept) | 2100 (Facebook) 734 (Instagram) (01 October to 31 December) | 388,291 (Facebook) 23,957 (Instagram)
Note on C18: Please note - reported are the numbers of plants PROPOGATED. Some plants don’t survive to the planting stage so this is not the number of plants that have been PLANTED. This data can be provided if required
Note on C19: Please note - reported are the numbers of plants PROPOGATED. Some plants don’t survive to the planting stage so this is not the number of plants that have been PLANTED. This data can be provided if required

## Workplan
[7 empty] | SIGNING |  | Year 1 (2021) | [15 empty] | Year 2 (2022) | [15 empty] | Year 3 (2023)
Activity/Task # |  | Complete | Who | Deadline | Cost | Nov |  | Dec | Jan |  | Feb | March | April | May |  | June | July | Aug |  | Sept | Oct | Nov |  | Dec | Jan |  | Feb | March | April | May |  | June | July | Aug |  | Sept | Oct | Nov |  | Dec | Jan |  | Feb | March | April | May |  | June | July | Aug |  | Sept | Oct | Nov |  | Dec
1 | Set-up Agreements and documentation
1.1 | develop Mon&Eval (KPIs and metrics) |  |  | 16-Nov, Mon
1.2 | feedback on Q&A |  |  | 16-Nov, Mon
1.3 | workplan |  |  | 16-Nov, Mon
1.4 | TV logistics (support accuracy) |  |  | 2020-11-17
1.5 | Finalise KPIs, species target lists, other (comms/staff engagement) |  |  | 19-Nov, Thu
1.6 | meet Botanica team |  |  | 23-Nov, Mon
1.7 | Finalise Collab Ag. Inc all deliverables (workplan, Mon&Eval, comms, staff engagement etc) |  |  | 24-Nov, Tue
1.8 | Sign Collab Agreement |  |  | 2020-12-02
1a | Ongoing meetings and documentation
1a.1 | project update meeting (max 1hr) |  |  | ongoing; monthly quick call | [5 empty] | 1 | [15 empty] | 1 | [15 empty] | 1
1a.2 | Technical Reports |  |  | ongoing; quarterly | [10 empty] | 1 |  |  |  | 1 |  |  |  | 2 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 2 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 2
1a.2 | Financial Reports |  |  | ongoing; 6months | [10 empty] | 1 |  |  |  | 1 |  |  |  | 2 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 2 | [7 empty] | 1 |  |  |  | 1 |  |  |  | 2
2 | Seed collection
2.1 | Reconnaissance & Collecting
2.2 | Corunna Daisy Specific
2.3 | Bussell’s Spider orchid Specific
2.4 | Omeo Stork's-bill Specific
3 | Seed germination trials
3.1 | Existing Collections
3.2 | New Collections
3.3 | Corunna Daisy Specific
3.4 | Bussell’s Spider orchid Specific
3.5 | Omeo Stork's-bill Specific
4 | Propagation & Re-introduction
4.1 | Propagation
4.2 | Re-introduction
4.3 | Corunna Daisy Specific
4.4 | Bussell’s Spider orchid Specific
4.5 | Omeo Stork's-bill Specific
5 | Comms & engagement
5.1 | content collection opportunities
5.2 | volunteering opportunities
5.3 | Botanic staff engagement opportunities
5.4 | Corunna Daisy Specific
5.5 | Bussell’s Spider orchid Specific
5.6 | Omeo Stork's-bill Specific
KEY
Major Deadlines
Tasks
Phases
Holidays
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will depend on what is collected and the time it takes to germinate and propagate so can be updated once we have the specific species identified.
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reflecting here that we have volunteers engaged in seed bank work all year round whether that is out collecting, cleaning and sorting seed, managing data, taking and databasing images etc.
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Happy to be guided by Botanica and when this is most appropriate to schedule in.